## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload documents (PDF, DOCX and TXT files) | MUST HAVE | None | Aarya | 3- Completed
Sprint 1 | Sprint 1 | US-02 | as a user I want to store my document's in vectors (numerical representations), for that I need a embedding model, and need to index documents and securely add the store data for future retrival | MUST HAVE | US-01 | Aarya | 3- Completed
Sprint 1 | Sprint 1 | US-03 | after inserting data as a user I need to retrive them safely and securely. | MUST HAVE | US-02 | Aarya | 3- Completed
Sprint 1 | Sprint 1 | US-04 | for handle easily and safely I need a UI (froentend) and UX. (chat interface) | MUST HAVE | US-03 | Aarya | 3- Completed
Sprint 2 | Sprint 2 | US-05 | as a user, I want to do Q&A with my documents for that need an enging (llm) that understand user questions and create queries from the searching DB storage, and then retrive the data with sources (citations), fo cross validation and fact-check | MUST HAVE | US-02 & US-03 | Aarya | 3- Completed
Sprint 2 | Sprint 2 | US-06 | as a user, I can able to upload multiple files with different file types such as text, docs and pdf. | MUST HAVE | US-01 to US-05 | Aarya | 3- Completed
Sprint 2 | Sprint 2 | US-07 | as a user, I aim to save time therefore i want Summarization of my upload documents | COULD HAVE | US-04 & US-05 | Aarya | 3- Completed
Sprint 2 | Sprint 2 | US-08 | As user, i aim want to control Output creativity and length of output. | COULD HAVE | US-04 & US-05 | Aarya | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a user I want Search into my documents So when Ask question The answer Is provided Also I like Precise answer Therefore I want To implement Different search methodologies. | SHOULD HAVE | US-01 to US-06, US-08 | Aarya | 3- Completed
Sprint 3 | Sprint 3 | US-10 | As a user I Want that Understanding My contex Memory, So that I can retrieve History Of questions when needed. | MUST HAVE | US-04 & US-05 | Aarya | 3- Completed
Sprint 3 | Sprint 3 | US-11 | as user for batter ux changes made in UI and add MD (markfile) upload and understanding. | MUST HAVE | US-01 to US-10 | Aarya | 3- Completed
Sprint 4 | Sprint 4 | US-12 | add clear chat button so that use can clear the chat and auto scrolling to lates chat for ease of uges, and as a use i want to swich automatically to a new model if old models limite is exceed | SHOULD HAVE | US-01 to US-11 | Aarya | 3- Completed
Sprint 4 | Sprint 4 | US-13 | as a use i want creator information, so that i can contact them if need. | COULD HAVE |  | Aarya | 3- Completed
Sprint 4 | Sprint 4 | US-14 | deployment on streamlit cloud, connect qdrant cloud for 24/7 uptime and perestiance | MUST HAVE | US-01 & US-13 | Aarya | 3- Completed
Note on F1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Insert document using local file system, code only |  |  | Aarya | Coding | 3- Completed | 2 | Day 1: 2
US-01 | T2 | Validate file formats (PDF, DOCX and TXT) |  |  | Aarya | Unit Test | 3- Completed | 0.5 | Day 1: 0.5
Note on D2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on K3: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on L3: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on M3: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on N3: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on O3: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on P3: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on Q3: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on R3: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on S3: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on T3: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on U3: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on V3: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on W3: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work
Note on I3: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on J3: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Development environment non set up | setup completed environment configuration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 |  |  | Aarya | Break tasks into smaller units | add only applicable code commits, note all | Daily code commits | Created task-level checklist
2 | Sprint 2 |  |  | Aarya
3 | Sprint 3 |  |  | Aarya
4 | Sprint 4 |  | 2026-02-10 | Aarya
5
6
7